IDEO Non-Profit

MEMORANDUM

To: Project Team Members

From: [Your Name]

Date: [Date]

CC:

Subject: Virtual Fundraising Gala for IDEO

I am pleased to write to you that we will be undertaking a project to organize a virtual fundraising gala for IDEO, a non-profit organization that is dedicated to creating a more inclusive world through innovative design solutions. The purpose of this memo is to provide an overview of the project, its objectives, responsibilities, and the resources we will need to accomplish our project goals.

Overview of the Project

The IDEO virtual fundraising gala is an opportunity to raise funds to support the organization’s mission, help them pay overhead costs, develop campaigns, and make improvements that will benefit their future client base. We plan on having the gala held on a live streaming platform and will feature a program similar to a live gala program, including speakers, inspirational videos, and a fundraising portion that will include clear calls to action to support the organization. The said gala will run between 60-90 minutes to keep the audience engaged, and achieve the goals set out for the project.

Outcomes: The outcome of the project is to successfully organize a virtual fundraising gala that engages IDEO's supporters and raises funds to support IDEO's mission and sustainability movement.

Overview of the Organization and Departments Involved

The project will involve various departments, including the Executive Director, Board of Directors, Marketing, The Staff, Volunteers, and Software Engineers. The Executive Director will provide the vision for the organization and inspire stakeholders to participate in raising the funds. The Board Members will be responsible for soliciting gifts from major donors and foundations. The Marketing Team and the Staff will use peer-to-peer marketing strategies, social media, and other grassroots efforts to spread the word about the event. The volunteers will be essential in reading and sending emails, monitoring social media posts, and sharing fundraising efforts with their network. Finally, the Software Engineers will be needed for the creation of the virtual fundraising platform or website being utilized for the gala.

Summary of Responsibilities

| Title | Responsibility |
| --- | --- |
| Executive Director | Provide guidance and support, and assist in identifying major donors and foundations. |
| Board Members | Assist in identifying major donors and foundations and help with fundraising efforts. |
| Marketing Team | Develop and implement a marketing campaign and provide support for the virtual fundraising gala. |
| Staff | Assist with the planning and execution of the virtual fundraising gala and provide support for marketing efforts |
| Volunteers | Assist with event logistics, social media monitoring, and fundraising efforts. |
| Software Engineers | Develop and set up the virtual fundraising platform or website. |

Goals and Objectives

- To raise $500,000 in donations during the virtual fundraising gala.

- To engage and educate the audience about IDEO's mission and sustainability movement.

- To increase IDEO's visibility and reach through social media and other marketing efforts.

- To provide a seamless and engaging virtual experience for attendees.

- To build and maintain positive relationships with major donors, corporations, and foundations.

Plan of Action

- Develop a detailed plan for the virtual fundraising gala, including a timeline, budget, and marketing strategy.

- Identify and engage major donors, corporations, and foundations.

- Develop and implement a social media and marketing campaign to reach out to potential donors and attendees.

- Set up a virtual fundraising platform or website that allows for a seamless and engaging experience for attendees.

- Recruit and train volunteers to assist with the event.

- Create a program for the virtual fundraising gala that includes speakers, videos, and calls to action.

IDEO’S Team Project

Project Organization Overview

| Project Plan | Identify | Analyze viability | Actualize the Plan |
| --- | --- | --- | --- |
| Project performance Management | Near Term vs. Long term | External Engagement | Virtual Platform |
| Project Execution | Legal Compliance | Implementation | Efficiency |

Project Milestones

| Milestone | Date |
| --- | --- |
| Develop a detailed plan for the virtual fundraising gala |  |
| Identify and engage major donors, corporations, and foundations |  |
| Develop and implement a marketing campaign |  |
| Set up a virtual fundraising platform or website |  |
| Recruit and train volunteers |  |
| Create a program for the virtual fundraising gala |  |

Project Performance Management

Near-Term

PPM will involve monitoring the progress of the project on a regular basis to ensure that it is on track to meet its short-term goals and objectives. This will include tracking the number of donors and funds raised, as well as assessing the effectiveness of marketing and outreach efforts. The project team will use data-driven insights to make adjustments to the project plan as needed and ensure that it stays on track.

Long-term

This step will involve assessing the overall success of the project in achieving its long-term goals and objectives. This will include measuring the impact of the project on the organization and its ability to continue to support its mission of creating a more just and inclusive world. The project team will use KPIs such as donor retention rates and the organization's overall fundraising success to assess the long-term impact of the virtual fundraising gala project. This will inform future fundraising efforts and the overall strategy of the organization.

Work Breakdown Structure for the IDEO Non-Profit Organization Virtual Fundraising

IDEO Virtual Fundraising

1. Project Initiation

3. Marketing and Communication Plan

2. Develop the Fundraising Strategy

4. Fundraising Activities

5. Donor Engagement and Recognition

6. Project Evaluation and Closure

1. Project Evaluation

1.1. Define project objectives and goals

1.2. Identify project stakeholders

1.3. Establish project scope

1.4. Develop project plan and timeline

2. Develop the Fundraising Strategy

2.1. Research fundraising strategies

2.2. Define target audience

2.3. Determine fundraising goals

2.4. Develop fundraising plan and timeline

4. Fundraising Activities

4.1. Plan and execute virtual events

4.2. Launch crowdfunding campaign

4.3. Plan and execute other fundraising initiatives

4.4. Manage and track donations

3. Marketing and Communication Plan

3.1. Develop a branding strategy

3.2. Create marketing materials

3.3. Define messaging and communication plan

3.4. Develop social media and email campaigns

5. Donor engagement and recognition

5.1. Develop a donor recognition program

5.2. Engage with donors regularly

5.3. Provide updates on project progress and outcomes

5.4. Thank donors and show appreciation

6. Project evaluation and closure

6.1. Evaluate project success against goals and objectives

6.2. Analyze fundraising results and return on investment

6.3. Develop recommendations for future fundraising initiatives

6.4. Close out the project and archive project documentsTop of Form

RACI Chart for IDEO Non-Profit Virtual Fundraising

| Task | Responsible | Accountable | Consulted | Informed |
| --- | --- | --- | --- | --- |
| Defining project objectives and goals | Project Manager | IDEO non-profit Director | IDEO non-profit Staff, Project Team Members | Stakeholders, IDEO non-profit Supporters |
| Identifying project stakeholders | Project Manager | IDEO non-profit Director | IDEO non-profit Staff, Project Team Members | Stakeholders, IDEO non-profit Supporters |
| Establishing the project scope | Project Manager | IDEO non-profit Director | IDEO non-profit Staff, Project Team Members | Stakeholders, IDEO non-profit Supporters |
| Developing project plan and timeline | Project Manager | IDEO non-profit Director | IDEO non-profit Staff, Project Team Members | Stakeholders, IDEO non-profit Supporters |
| Research fundraising strategies | Project Team Members | Project Manager | IDEO non-profit Staff, External Fundraising Experts | IDEO non-profit Director, Stakeholders |
| Defining the target audience | Project Manager | Project Team Members | IDEO non-profit Staff, External Fundraising Experts | IDEO non-profit Director, Stakeholders |
| Determining the fundraising goals | Project Manager | Project Team Members | IDEO non-profit Staff, External Fundraising Experts | IDEO non-profit Director, Stakeholders |
| Developing a fundraising plan and timeline | Project Manager | Project Team Members | IDEO non-profit Staff, External Fundraising Experts | IDEO non-profit Director, Stakeholders |
| Developing the branding strategy | Project Team Members | Project Manager | IDEO non-profit Staff, External Marketing Experts | IDEO non-profit Director, Stakeholders |
| Creating the marketing materials | Project Team Members | Project Managers | IDEO non-profit Staff, External Marketing Experts | IDEO non-profit Director, Stakeholders |
| Define messaging and communication plan. | Project Team Members | Project Manager | IDEO non-profit Staff, External Marketing Experts | IDEO non-profit Director, Stakeholders |
| Develop social media and email campaigns. | Project Team Members | Project Manager | IDEO non-profit Staff, External Marketing Experts | IDEO non-profit Director, Stakeholders |
| Plan and execute virtual events | Project Team Members | Project Manager | IDEO non-profit Staff, External Event Planners | IDEO non-profit Director, Stakeholders |
| Launch crowdfunding campaign | Project Team Members | Project Manager | IDEO non-profit Staff, External Crowdfunding Platform | IDEO non-profit Director, Stakeholders |
| Plan and execute other fundraising initiatives. | Project Team Members | Project Manager | IDEO non-profit Staff, External Fundraising Experts | IDEO non-profit Director, Stakeholders |
| Manage and track donations. | Project Team Members | Project Manager | IDEO non-profit Staff, External Financial Experts | IDEO non-profit Director, Stakeholders |
| Develop a donor recognition program. | Project Manager | Project Team Members | IDEO non-profit Staff, External Donor Recognition Experts | IDEO non-profit Director, Stakeholders |
| Engage with donors regularly. | Project Team Members | Project Manager | IDEO non-profit Staff, External Donor Engagement Experts | IDEO non-profit Director, Stakeholders |
| Provide updates on project progress and outcomes. | Project Manager | Project Team Members | IDEO non-profit Staff, External Communication Experts | IDEO non-profit Director, Stakeholders |
| Thank donors and show appreciation | Project Team Members | Project Manager | IDEO non-profit Staff, External Donor Appreciation Experts | IDEO |

Top of Form

Identification of Resources

To accomplish our goals, we will need the following resources:

- P. Hyer - Director: To specify goals and guidelines for gala

- S. Berger - Head of Global Marketing: To be apprised of goals and specifications and to create a plan for individual marketing staff and volunteers

- Software design staff: To help set up the live stream platform for the gala

- Executive Director, Board Members, Staff, Volunteers, and social media: To be used to compile donor/attendee list.

This project is still in the infancy stage within the organization, and we have a lot of work ahead of us. However, with the support of the project team members, we are confident that we can achieve our objectives and make a meaningful impact on IDEO's mission. I look forward to working with each of you on this exciting project.

If you have any questions or concerns, please do not hesitate to contact me.

Best regards,

[Your Name]

Top of Form